## NGD - Perfromance
Jira Story Id | ACT | Perf Optimization | Status | Owner | Release | Comments | Sprint | Production Status Post ER 10/15
NEXTGEN-4162 | ACT-108 | 1) Configurator streaming - AAL & NSE - | In Prod | Srikrishna Gumma/Jayakumar Shanmugam | 2025-10-29 | Create tech enabler story for configurator Currently Smartwatch streaming is enabled in prod Document approach , testing approach and backout 10/17 - Testing in progress in lower. Plan for 10/24 prod NSE and AAL | 101 | 11/5 - On track Enabled on Canary
NEXTGEN-4067 | ACT-108 | 2) Add plan along with device - AAL & NSE | In System Testing | Asutosa Sahoo/Kunal Gupta | 2025-12-03 | NSE changes part of NEXTGEN-4067 Need Separate testing story for AAL 9/25: This was discussed today and AAL and NSE changes will be taken care of for 10/15 10/13: Issue found on Canary during testing and currently disabled on canary.Prakash working on the fix 10/17 - Target 10/24 11/19 - Fix Tarted post Thanks Giving 11/25: All the fixes are done and need QA to expedite the testing.
ACT56-7634 | ACT-56 | 3) Flyout cart modal component from PDP | In Prod | Alap Kothari | 2025-10-15 | Dev Completed and aligned for 10/15. Need extensive testing on all platforms(MVA App) 10/13: This is going live with 10/15 |  | Enabled
To be created | ACT-56 | 4) Flyout modal server side rendering | In Prod | Alap Kothari | 2025-10-15 | Alap to share the story for this change |  | Enabled
To be created | ACT-81 | 9) New number page optimization - NSE & AAL | In Prod | Kunal Gupta/Khushboo Kumari | 2025-10-15 | Rahul to review the changes with Kunal and Prakash 9/24 : PR was shared with Kunal, Kunal to get back on it 9/29- Kunal is getting this reviewed internally with other key folks. He is good with the changes |  | Enabled
ONEAPP-20593 | ACT-46 | 10) Multi line configurator streaming & optimization - EUP | In Prod | Sumit Khemraj Gabhane | 2025-10-24 | Sumit to provide an offline update on multi-line configurator streaming and operations by noon tomorrow 9/24 : No Update 9/29: Added the ticket aligned for 10/15. 10/13 : As per Sudhakar , there are some functional issues .If we fix it before 10/15, 10% throttle willbe enabled. Otherwise it will be next immediate release.. 10/17 - Target 10/24 10/23: , enabling 50% with 10/24 on Prod |  | Enabled 100% on 11/5
PRFX-4894 | ACT-81 | 5) Removal of MInicart api after add protection - EUP | In Prod | Rahul Vishnu Khandelwal | 2025-10-29 | Simranjit and Ashwin to discuss this further and provide an update 9/25: Based on the discussion with Simranjit.This is yet to be discussed with Ashwin and will get an update by Monday(9/29) Discussed with Rohan Kumar, mini-cart-summmary api will be removed, ETA is pending. This was aligned for 10/15 by Sudhakara and team but was not picked up and now ACT-81 is picking it up for 10/29 release 10/17 - "In System Testing and with QA Testing is required from Product team as well" 10/29 : Enabled in Production |  | Enabled
| ACT-54 | 12) Removing of getProcessStep in fluyout cart | In Prod | Asutosa Sahoo Alap Kothari | 2025-10-17 | There is no release on 10/22,so updated the release to 10/29 10/17 - Tesing in prod pending |  | Enabled
To be created | ACT-54 and 46 | Get checkout details optimization Delivery & Payment page - AAL & EUP" with "ACT-46 ?" | In review | Rohan Kumar Asutosa Sahoo | TBD | This will be taken care as part of redesign 2-3 Sprint work. Fullfillment checkout redesign 11/25 : Asutosa Sahoo to get back on this by 12/5
PRODDEF-55252 | ACT-107 | 7) PDP product images carousel - can we make this SSR (VDS depdendency) | In Prod | Sanjeev Kumar Chauhan Jayakumar Shanmugam | TBD | Can we make this SSR ? / VDS Dependency ? Jayakumar to follow up on this Sanjeev - 24 Sep- Its a VDS component and we already asked VDS team to make it render in Server side during integration but they mentioned it can't/will not be done. Sanjeev- 25th -Raised fresh ticket with VDS for solving this Jayakumar Shanmugam Please double check with VDs-- As per Jayakumar Shanmugam this cannot be done from VDS servverside 10/17 - VDS updated, and this was moved to canary. Srikrishna Gumma and Sanjeev Kumar Chauhan to confirm if this is on canary and enabled 10/28 Anil on Jira : The jump section was added by Target team and this test was stopped mid OCT. No fix done by application team for this Target team removed jump section in mid of OCT, exact date we are not sure. This was due to target team added jump section and in mid oct they removed, there was no code fix done from GTS
To be created | ACT-81 | 8) Down payment page optimization - NSE | Pending Discussion | Narender Parmar | TBD | Rahul Vishnu Khandelwal to connect with Kunal to finalize the approach 9/24: Discussion b/w rahul and Kunal is done, Need to discuss this with Soma to finalize the approach Planning to close the discussion by 9/25 Approach is not finalized for this ticket 10/17 : Narendra to discuss with Deepak and come back with the final approach 11/25: Shalini to discuss and close this out with Soma
NGDII-1374 | ACT-54 | 11) Remove oneclick in Assign MTN | In Progress | Asutosa Sahoo | 2025-12-03 | Asu to follow up with CXP platform team 9/24 : No update 9/25:There is a call scheduled to discuss this with CXP platform team tomorrow.More updates to follow tomorrow 10/17: CJCM has not started on this. Asu to come back with the latest. Need discussion with Platform Team 11/25 : All the changes are completed. Testing to start from 11/26.
To be created | Across ACTs | Partial prerender - Header/Footer and CQ calls during runtime - Update the layouts to execute the calls for header/ footer / cq content during build time to enable partial prerender | Parked | Srikrishna Gumma | Q1 26 | 10/17: Framework is partially supported, post migration to next JS 16 version, this an be picked up
GTSGR-408004 | SRE | Enable Streaming in Prod | In Progress | Srikrishna Gumma | 2025-12-03
NEXTGEN-3379 | 108 | Streaming Changes for Cart (AAL and NSE) | In Progress | Srikrishna Gumma | 2025-12-03
| ? | Streaming changes for Delivery | In Progress | ? | ?
| ACT-46 | Streaming changes for EUP Configurator |  | Rohan Kumar
CXTDT-797911 | ACT-108 | Flyout cart Optimization NSE flow | In Progress | Gupta Kunal | 2025-12-10
| ACT-46 | Streaming changes for Cart EUP Flow |  | Sudhakara Hanumantharayappa | TBD

## Tech Debt
Category | Topic | Description | Owner | Status | JIRA # | Due Date | Comments
Foundation | Add /sales to browse | Browse needs to update the path to nextgendigital/sales/browse ingress ticket - for updating the IG & APIGEE ticket to update the browse path | Rohan Kumar Sanjeev Kumar Chauhan | Done |  |  | sanjeev- 11 Apr Done on QA2 , Canary, Prod. Pending for QA3/QA30/Dit3 GTSGR-323826
Foundation | Auth Flow Changes | Create IG/APIGEE ticket to for auth scenarios nextgendigital/sales/*/auth UI changes requires to enable Auth calls from server side JWT validation on the server pages | Srikrishna Gumma | Done |  |  | IAMIFG-5516 - IG GTSGR-322726 - Apigee 4/10 - Code change in progress by Gumma 4/21 - Gumma to share update , are changes in prod ? any code changes pending ? 4/21 - Framework changes to handle auth are completed from Next.js/IG/APIGEE 4/21 - IG/APIGEE changes are targetted for production with the upcoming ER.
Architecture | Streaming E2E | 1. Follow up on streaming and get this working 2. What sections are we going to stream for PDP, Configurator 3. Logged in PDP should we do stream or get from cache ? | Srikrishna Gumma | Done |  | 25.07 | 4/21 - Waiting on changes from IG. Rajneesh already escalated to Sr Dr as of 4/18 4/21 - Rohan to update PDP streaming POV in the deck 4/21 - Slide added. 4/24 - IG Confirmed changes are ready for testing. Gumma validated changes in QA2 an confirmed its working Need to create tech debt stories for streaming implementation Ask IG to propogate changes to SIT1, SIT3 4/28 - Pending changes in SIT1, SIT3. ETA - 4/29 5/1 - T1, T2 Done , 5/6 - T3 IG Changes pending 5/14- Streaming working in QA3 5/27 - Srikrishna Gumma are streaming changes pushed to prod for IG and Apigee ?
Architecture | Streaming Chanes for Configurator |  | Srikrishna Gumma | Done | NEXTGEN-3426 | 25.07 | Aligned with release 7/11 for dark testing 7/22 - Code is in Dark in Prod. Wiating for IG changes to be deployed to Canary - No ETA yet from IG
Monitoring | Prod CDN logs not streaming to Newrelic , elastic |  | Srikar Reddy Guda | Done |  |  | As per Chita, sre team is working on this ETA was 4/16. Changes are still not done 4/21 - New ETA Provided by Chita 4/23 4/28, 5/1 - Changes are available https://onevzakamai-nextgen-kibana.verizon.com/app/discover , dont have access to kibana. Reached out to Chita 5/29 - Create dashboard - for errors and perf
Monitoring | Faro Dashboard | Faro dashboard to be setup in SRE Dashboard | SRE / Srikar Reddy Guda | Done |  | 25.06 | 4//22 1. Faro data is captured and logged to kibana currently via jsnotify. 2. SRE team will consume this data and create RUM SRE Dashboard. 3. Dev Team to Share the documentation on metrics to be reported https://oneconfluence.verizon.com/display/NextGenDigital/7.+Graphana+Faro+Dashboard 4. SRE Team the analyse faro logs and come up with integration approach 5/1 - Follow up call setup with SRE on non Prod on 5/5 5/6 - Met with SRE team and shared logs for analysis. Follow up meeting on 5/8 5/29 - Need follow up meeting with SRE 06/06 - Had a meeting with Sre team. They started working on it and need more 2 weeks to finish. Follow up meetings scheduled every friday 9AM ET until completion
Monitoring | Faro data retention | 1. Create a different index , 2. Can we push this to redshift ? | Rohan Kumar | On Hold | GTSGR-348488 |  | SRE contact Sivaram for Redshift 4/22 Reached out to Sivarama Thallam, @Sakthivel Pandiyan Ponraj 4/23 - Discussed with Sakthi for new index for PERF. Need to create a new ticket , there is will be funding required for additional storage and need to work with Sankara. 4/30 - Request submitted by Sankara 5/8 The indices that we have today are based out of the logType that the app is printing. All logType "audit" go to hivv_onevz_nsasoe_adt* index and logType "log" to hivv_onevz_nsasoe_log* index. Please make the necessary changes to append logType "perf" to all logs that you are intending to ship to a separate perf index and let us know so that we can modify our shipper configs accordingly. Also, create a GTSGR ticket (PCT 191) to track this effort. GTSGR-335649 5/15 - Will take this up once separate log index is created
Monitoring | Faro | Need to capture resourses js / css metrics | Srikrishna Gumma | Done |  | 25.05 | 4/23 - Code Fix in progress by Srikrishna Gumma 4/24 - Gumma is working on this , its triggering jsnotify for all the assets 4/29 - Changes available in SIT
Monitoring | ML Order Grafana report Update |  | Srikar Reddy Guda | Done |  |  | https://techopsgrafana-awseast.verizon.com/d/wSvVc8EMz/mobility-digital-e2e-page-funnel?orgId=48&from=now-1h&to=now
PERF | Faro logging update | Fix the duration calculation to read from previous page, to current page. Also use custom marker to read the duration, instead of waiting of pageLoad to complete, page load includes all the assets including third party. | Srikrishna Gumma/ Ankush Saini | In Production | NEXTGEN-3425 | TBD | Needs Sprint Algnment ashwin.raj@publicissapient.com
Monitoring | Multiple Calls from Faro introduces load to IG , Apigeee Load | Need merge all calls to one | Srikrishna Gumma | Done |  | 25.05 | 4/22 - Rohan Kumar Srikrishna Gumma- can this be addressed via a code fix ? 4/24 - Code fix in progress by Gumma 4/29 - Changes available in SIT
Monitoring | Dashboards and logging | check existing dashboard and we are logging all params like flow name etc for logged in flow as well. Create non prod dashboards | Srikar Reddy Guda | Done |  |  | Srikar Reddy Guda- did we chek this ? Need to update all Grafanna and Kiabana dashboard for logged in flow Error, Funnel, Monitoring - ETA for non prod 4/25 4/24 - non prod monitoring dashboard changes to be done by 4/25 - Srikar NGD Non Prod: https://onevzsoelogs-np.ebiz.verizon.com/_dashboards/goto/4137826ec1e2ac71ca898a9fed0598a4?security_tenant=global
PERF | Sitespeed scrit for ML - Non Prod |  | Kunal Gupta | Done |  |  | 4/29 - Kunal to reach out to SS Team to setup non prod script for ML 5/6 - Non prod setup done http://10.74.182.67/Results/QA1/2025-05-06/NGDMultiLineProspect/
PERF | Slowness in CDN Assests |  | Jayakumar Shanmugam Ashwin Raj | Closed |  |  | AKAM-CASE #F-CS-9455538 4/10 - As per Akamai response : 59.33% of requests were served in 0ms, indicating cache hits where Akamai delivered content directly from the cache without needing to contact the origin. 32.61% of requests were served in under 50ms, demonstrating that Akamai’s caching is highly efficient. A small portion of requests (6.68%) took slightly longer (50ms-100ms), likely due to minor network factors or cache retrieval times. 4/18 - Ticket is closed , as per Akamai there are no major issues. As of now the akamai logs are not rolling to Newrelic so we dont have enough live data to show assets are slow, only able to test via browser. Need to assess this again once akamai log streaming is working
PERF | Static assests in protection, number selection not getting cached, checkout | Need a code fix | Srikrishna Gumma | Done |  |  | 4/21 - Code Fix done by Gumma . Will target for coming ER 4/24 - Changes deployed to Prod. All assests in checkout and configurator MFE will get chached now , except page and layout related js 5/1 -
PERF | Add condition for page and layout to be cached in CDN |  | Srikrishna Gumma | Done
PERF | Next.js Load Test , especially for ML | Need to do a Next.js profiling in local first and then in non prod for performance | Sanjeev Kumar Chauhan | Done |  |  | Need to create a story for this. This will take minimum one sprint 4/21 - Need update from Khushboo 4/29 - Do a lighthouse profiling in local / SIT. Sanjeev to work with team. 5/11 is the next LT , need to do this before that. Can we get the expected traffic for ML - check with business (Ashwin/Prakash) 5/1 - Try a load test in local with NPM module and mock data. Get current POD config from SRE 5/8 - Not prod LT ETA today ? load test done in prod and non pord
PERF | HTTP 2 Client |  | Sanjeev Kumar Chauhan | In Progress |  |  | We are not using this currently. This can not be wrapped with a feature flag. We would need to use separate packages at the framework level. Sanjeev Kumar Chauhan - Can we plan for this change and get a tech enabler story created for this 4/24 - Need update from Sanjeev on HTTP2 For Connection Pool Below is the NextJs /NodeJs http agent configuration with default values httpAgentOptions: { keepAlive: <value>, // default TRUE keepAliveMsecs: <value>, // Optional: default is 5000 , Set keep-alive timeout in MS maxSockets: <value>, // Optional: default is Infinity , Controls the maximum number of concurrent connections that can be open to a specific host. maxFreeSockets: <value>, // Optional: default is 256 , Set maximum number of idle sockets timeout: <value>, // Optional: Set socket timeout in milliseconds } 4/29 - Sanjeev to further explore on this and come back with a POV / Next Step 5/1 - Create a conflunce page with all the config which we can tune for performance ( next/ node / eks)
PERF | NGD Cart Page SRE Score is Slows | CXTDT-701043 | Jayakumar Shanmugam Kunal Gupta | Done |  |  | 4/29 - whats the next step on this ? Jayakumar Shanmugam 5/15 - To be validated after 5/21 . Fix for synch in progress
PERF | NGD ML Sitespeed non prod script |  | Kunal Gupta | Done |  |  | http://10.74.182.67/Results/QA1/2025-05-14/NGDMultiLineProspect/
PERF | NGD Multi lIne sre script for non prod and prod pilot |  | Jayakumar Shanmugam | Done |  |  | SRE is working on non prod Infra setup for SRE Dashboard. Requested to setup in pilot Jayakumar Shanmugam to Work with SRE , ETA 5/19
PERF | NGD PDP SRE Script for non prod and prod pilot |  | Kunal Gupta | Done |  |  | SRE is working on non prod Infra setup for SRE Dashboard. Requested to setup in pilot 4/18 - Details shared with SRE team. ETA April 23 4/24 - PDP Pilot setup complete https://vcgsre.verizon.com/sredashboard/flows/digital-sales-and-services-desktop/NGD-PDP/3893064?env=Prod-Pilot
PERF | Fly out cart to Configurator is slow |  | Srikar Reddy Guda | Done |  |  | 4/29 - Srikar to share the analysis Its a data issue in QA env. The default zipcode 94203 was giving an error - CART_ZIPCODE_DATA_NOT_AVAILABLE causing the delay. If we load with another zipcode like 30004, the flyout cart loads quick. Sample e2e Id with valid zip took 1100 ms - c9143efb-d826-4ac3-9aa1-179b3197c963-149978 Sample e2eId with no zip downstream took 15713 ms- 01adc54d-0dbb-4e4b-85a9-777d9b9f7024-1357470
PERF | Partial prerender - Header/Footer and CQ calls during runtime | Update the layouts to execute the calls for header/ footer / cq content during build time to enable partial prerender | Srikrishna Gumma | Not Started | NEXTGEN-3427 | TBD | 4/30 -Srikrishna Gumma - whats the effort for this ? 5/ 8 - 3-4 days effort as per Gumma
Throttling | Edge workers - GW/PDP Throttling | This is for throttling and Rohan is working on this | Rohan Kumar | Done |  |  | 4/10 - Code Changes deployed in EdgeWorkers. Routing is working. Throttling using FFLag not working , SRE need to fix this. Is there a ticket Rohan Kumar ? Alternate approach is to call cradle api for throttling from Edgeworker 4/17 - Edge worker rediretion and call to FFlag is working 5/1 - Enabled on non Prod
Throttling | Kill Switch Approach for Enabling/ Disabling Edgeworker Throttling without going through a CMD/ CA etc |  | Rohan Kumar | Done |  |  | 5/15 - There is no effective kill switch without a CMD. Will document this and has been discussed in mini forums. Will get all together and get it aligned. 6/5 - All testing prior to Prod Go live will be done with Staging. If any direct issues in Prod Live will need to be killed through Akamai config.
Throttling | FFlag Throttling not woking |  | SRE | Closed |  |  | Whats the next step on this ? 4/21 - Rohan to check with Simran on this 4/24 - SRE Team is working on prospect FFlag Throttling 4/26 - We will use Cradle for now for throttling. 5/1 - Rohan to discuss and confirm the approach This has been discussed with SRE multiple times , there will not be any new capabilities added at this point other than whts supported for new customer
Throttling | Non Prod Cradle throttling on PDP |  | Rohan Kumar | Done |  |  | 4/24 - Cradle ticket to be created by Rohan. 4/25 - Cradle config ticket created - https://onejira.verizon.com/browse/NSADT-180583 5/1 - Ticket to be followed up with Cradle team 5/15 - Testing in progress with Edgeworker and cradle config before opening it for all. 6/5 - Non Prod throttling is working fine.
Throttling | Edge workers - CICD Setup | Edge workers - CICD Setup | Rohan Kumar | On Hold |  |  | 4/18 - https://onejira.verizon.com/browse/GTSGR-329030. 4/21 - Ticket created for discussion with Felssy today. 4/21 - No one joined from Felssy's team. Sent a note on slack to the group setting context and confluence document to refer the steps to setup pipeline to deploy on Edgeworkers. https://oneconfluence.verizon.com/display/NextGenDigital/3.3.2+-+Throttling+using+Akamai+Edgeworkers 4/25 - Felssy and team workin in this ETA - ? 4/28 - JIRA tickets for New pipeline and repo https://onejira.verizon.com/browse/GTSGR-329030 - Repo https://onejira.verizon.com/browse/GTSGR-331630 - Pipeline 5/1 - Follow up meeting setup today 5/15 - Manual deployments to continue for now. Art mentioned he was able to work on a solution and is able to deploy and activate using api's. He will try and work on an tool to upload the bundle. So it will be a hybrid approach, partly automated. 6/5 - Manual deployments to continue through Art.
Throttling | Logged in PDP AAL/EUP Throttling | Once the uses logs in from NGD PDP how do we throttle AAL/EUP to BAU ? | Rohan Kumar | Done |  |  | 4/21 - Rohan to Document the approach today and review on 4/22 4/21 - Throttling use cases documented in https://oneconfluence.verizon.com/pages/viewpage.action?pageId=1523843643 4/28 - Cradle will be used to throttle Logged in using mtn ending with last 2 digits. 5/15 - EUP flow will possibly go live before NGD PDP NSE and AAL. They have a very specific use case to throttle which got implemented on 5/14. Will update the document accordingly. 6/5 - Canary Staging testing done and changes have been made live.as per Jeremy today. Jeremy/Art to confirm if its enabled for live traffic from 4 states on Canary.
Code | NGD Common Components |  | Khushboo Kumari | In Progress |  |  | Gumma is working on Plans / Perks / Acc along with Ankush 4/22 - accessory tile is ready for common component migration plans and perks are being created by ACT-45 (Sumit) and will incorportate the components once they expose the components 4/29 - Guidelines to be created for reuseability - Sanjeev
Code | Are we handling session expiry scenario for client side auth api calls | Handle the expired requests to handle and redirect to AM login page for the client side calls Verify and make necessary changes to Session time out modal to handle the Auth flows | Jayakumar Shanmugam Srinivas Govuri | Not Started
Code | Cart related log errors are getting logged under configurator from jsnotify. All new pages in configurator MFE should be logged with proper page name |  | Srikrishna Gumma | Done | NEXTGEN-3428 | 25.07 | SP - 1
Code | FFLag Clean up |  | Prakash Karnati Kunal Gupta | Done | NEXTGEN-3424 | 25.07 | 4/29 - Story to be created in next sprint. Kunal / Prakash to discuss and identify FFlags to be cleaned up.

## SRE
App | Task | Status | Team | Owner | Due Date | Updated Due date | Ticket | Comments | Next Step
Common | Common Repo Creation | Done | SRE |  | 2024-05-03
Common | Jfrog Artifactory Setup for common code | Done | Dev Team | Rohan Kumar | 2024-05-03
IG | /NGD Routing (OPENIG) - DIT1 | Done | IG | Rajesh Mathiyalagan | 2024-05-15 | 2024-05-27 | /IAMIFG-2906 | Done
IG | /NGD Routing (OPENIG) - DIT2 | Done | IG | Rajesh Mathiyalagan |  |  | /IAMIFG-2906 | Done
IG | /NGD Routing (OPENIG) - DIT3 | Done | IG | Rajesh Mathiyalagan | 2024-05-15 | 2024-05-27 | /IAMIFG-2906 | Done
IG | /NGD Routing (OPENIG) -SIT1 | Done | IG | Rajesh Mathiyalagan |  |  | /IAMIFG-2906 | Done
IG | /NGD Routing (OPENIG) - SIT 2 | Done | IG | Rajesh Mathiyalagan |  |  | /IAMIFG-2906 | Done
IG | /NGD Routing (OPENIG) - SIT3 | Done | IG | Rajesh Mathiyalagan | 2024-05-15 |  | /IAMIFG-2906 | Done and validated
IG | /NGD Routing (OPENIG) - DIT 4,5 | Not Started | IG | Rajesh Mathiyalagan | TBD | 2024-06-03 | /IAMIFG-2906
IG | /NGD Routing (OPENIG) - SIT 4,5 | Not Started | IG | Rajesh Mathiyalagan | TBD | 2024-06-03 | /IAMIFG-2906
Apigee | /NGD Routing (Apigee) - DIT / SIT | Done | Apigee | Vijender PingiliDivya Chaitanya Prabhu Barlapudi | 2024-05-15 |  | DIGIP-652
Webserver | Web Server Reverse Proxy DIT1 | Done | SRE Middleware | Rohith Kumar |  |  | GTSGR-235965 | 7/11 - Code need to be manually deployed , assigned ticket to sre middleware 7/9 - Check ticket for urls not working
Webserver | Web Server Reverse Proxy SIT1 | Done | SRE Middleware | Rohith Kumar |  |  | GTSGR-235965 | 7/11 - Code need to be manually deployed , assigned ticket to sre middleware 7/9 - Check ticket for urls not working
Webserver | Web Server Reverse Proxy DIT2 | Done | SRE Middleware | Rohith Kumar | 2024-05-27 |  | GTSGR-235983
Webserver | Web Server Reverse Proxy SIT2 | Done | SRE Middleware | Rohith Kumar | 2024-05-27 |  | GTSGR-220626 | Working
Webserver | Web Server Reverse Proxy DIT3 | Done | SRE Middleware | Rohith Kumar |  |  | GTSGR-235926 | 7/16 - All URLSs are working 7/11 DIT URLS are still not working https://vzwqa7.verizonwireless.com/nextgendigital/sales/checkout/health https://vzwqa7.verizonwireless.com/nextgendigital/sales/configurator/health 7/9 - Check ticket for urls not working 6/2 - Not working https://vzwqa7.verizonwireless.com/nextgendigital/sales/configurator/health https://vzwqa7.verizonwireless.com/nextgendigital/sales/checkout/health |  | GTSGR-220626
Webserver | Web Server Reverse Proxy SIT3 | Done | SRE Middleware | Rohith Kumar |  |  | GTSGR-235926 | 7/9 - Check ticket for urls not working 7/2 - Not working https://vzwqa3.verizonwireless.com/nextgendigital/sales/checkout/health https://vzwqa3.verizonwireless.com/nextgendigital/sales/checkout/health
Browse MFE | Browse Repo Creation | Done | SRE Pipeline |  |  |  | GTSGR-195909
Browse MFE | Browse MFE Build Job | Done | SRE Pipeline |  |  | 2024-05-09 | GTSGR-195909 | Done
Browse MFE | Browse MFE Deploy Job | Done | SRE Pipeline | Hajera Nasreen Kasim Razvi | 2024-05-02 |  | GTSGR-195909
Browse MFE | Browse MFE EKS Setup T1 | Done | SRE Pipeline | Hajera Nasreen Kasim Razvi | 2024-05-17 | 2024-05-29 |  | Done
Browse MFE | Browse MFE EKS Setup T2 | Done | SRE Pipeline | Saroj Ranjan Panda |  |  |  | Done
Browse MFE | Browse MFE EKS Setup DIT3 | Done | SRE Pipeline | Hajera Nasreen Kasim Razvi | 2024-05-02 |  | GTSGR-195909 | Done
Browse MFE | Browse MFE EKS Setup SIT3 | Done | SRE Pipeline | Hajera Nasreen Kasim Razvi | 2024-05-06 | 2024-05-09 | GTSGR-195909 | Done
Browse MFE | Browse MFE EKS Setup T4 | Done |  | Saroj Ranjan Panda |  |  |  | Done
Browse MFE | Browse MFE EKS Setup T5 | Not Started | SRE Pipeline | Saroj Ranjan Panda |  |  |  | Won't be deployed in T5 because we don't have the DIT5
Browse MFE | Browse MFE Unit Testing Pipeline setup | Done | SRE Pipeline | Hajera Nasreen Kasim Razvi | 2024-05-10 | 2024-05-20 |  | 5/20 - Unit testing for browse is running
Browse MFE | Browse MFE Sonar setup on Pipeline | Done | SRE Pipeline | Hajera Nasreen Kasim Razvi | 2024-05-10 | 2024-05-20 | GTSGR-195909 | Done
Browse MFE | Browse MFE fortify setup on Pipeline | Done | SRE Pipeline | Hajera Nasreen Kasim Razvi | 2024-05-10 |  |  | Done
Browse MFE | Browse MFE Sysdig - Image Scanning | Done | SRE Pipeline | Hajera Nasreen Kasim Razvi | 2024-05-10 |  |  | Nasreen to check with Sasha
Browse MFE | Browse MFE Repo Trunk based setup (build and deploy) | NA | SRE Pipeline | Hajera Nasreen Kasim Razvi | 2024-05-10 | 2024-06-30 | GTSGR-195909 | 7/8 - Will set this up once browse is in scope 6/25 - Yet to be setup
Configurator MFE | Configurator Repo Creation | Done | SRE Pipeline |  |  |  | GTSGR-195909
Configurator MFE | Configurator MFE Build Job | Done | SRE Pipeline | Hajera Nasreen Kasim Razvi | 2024-05-03 |  | GTSGR-195909
Configurator MFE | Configurator MFE Deploy Setup | Done | SRE Pipeline | Hajera Nasreen Kasim Razvi | 2024-05-03 |  | GTSGR-195909
Configurator MFE | Configurator MFE EKS Setup T1 (DIT and SIT) | Done | SRE Pipeline | Hajera Nasreen Kasim Razvi | 2024-05-17 | 2024-05-21 |  | Done | Dinesh to complete.
Configurator MFE | Configurator MFE EKS Setup T2 (DIT and SIT) | Done | SRE Pipeline | Saroj Ranjan Panda | 2024-05-28 |  |  | Done
Configurator MFE | Configurator MFE EKS Setup T3 (DIT and SIT) | Done | SRE Pipeline | Hajera Nasreen Kasim Razvi | 2024-05-03 | 2024-05-09 | GTSGR-195909 | Done | https://soe-hivv-nsdit2.ebiz.verizon.com/ngd/sales/configurator
Configurator MFE | Configurator MFE EKS Setup T4 (DIT and SIT) | Done | SRE Pipeline | Saroj Ranjan Panda | 2024-05-28 |  |  | Done
Configurator MFE | Configurator MFE EKS Setup T5 (DIT and SIT) | Not Started | SRE Pipeline | Saroj Ranjan Panda | 2024-05-28 |  |  | Won't be deployed in T5 because we don't have the DIT5
Configurator MFE | Configurator Scheduler for DIT3/SIT3 | Done | SRE Pipeline | Saroj Ranjan Panda | 2024-05-09 | 2024-05-09 |  | Done
Configurator MFE | Configurator MFE Unit Testing Pipeline setup | Done | SRE Pipeline | Hajera Nasreen Kasim Razvi | 2024-05-10 | 2024-05-15 | GTSGR-195909 | Done
Configurator MFE | Configurator MFE Sonar setup on Pipeline | Done | SRE Pipeline | Hajera Nasreen Kasim Razvi | 2024-05-10 | 2024-05-14 | GTSGR-195909 | 5/21 - Sonar dashboard setup https://onesonarcloud.verizon.com/dashboard?branch=release%2F24.07.100&id=VZW_CV9V_onevz-soe-digital-ngd-configurator
Configurator MFE | Configurator MFE fortify setup on Pipeline | Done | SRE Pipeline | Aleksandar Sasha Zivojinovic | 2024-05-10 | 2024-05-14 | GTSGR-195909 | Done | Dev team to validate.
Configurator MFE | Configurator MFE Sysdig - Image Scanning | Done | SRE Pipeline | Aleksandar Sasha Zivojinovic | 2024-05-10 | 2024-05-14 | GTSGR-195909 | Done
Configurator MFE | Continious Deployment to DIT | Done | SRE Pipeline | Hajera Nasreen Kasim Razvi | TBD
https://docs.google.com/spreadsheets/d/1DF-mxyGuSIOQQDiyy8fV8W-QhvQgOeIhUF2yudndiUw/edit?gid=59612488#gid=59612488 | Brand request for /nextgendigital/ context path | Done | Brand | Ashwin Raj | 2024-05-09 |  | URL Request #: UR-2451122 Requested URL: verizon.com/nextgendigital | Done | Context path /nextgendigital approved by branding
All MFE | Add NGD Projects to Fortify Dashboard | Done | Dev Team | Divya Chaitanya Prabhu Barlapudi | 2024-06-21 |  |  | Chaitanya is working on this
All MFE | "Size Limit" Setup for Browse and Configurator, Checkout MFE (Asset size) | Done | NSA Enablement | Amer Khan | 2024-05-17 | 2024-06-30 |  | 7/2 - Wating for code merge 7/1 - Nishant working with Felssy's team to resolve merge conflict 6/27,28 - Waiting for Felssy to merge the code 6/26 - Gosikan to confirm once code is merged and enabled for. NGD Repo to validate 6/25 - Dev complete, Code to be merged to main brnach and tested. 6/24 - Updates from Amer - incorporating few change per felsy to size limit to check for existance, syntax issues 6/21 - Changes in 8./100 looks good, need to enable for 9.100 for configurator and checkout 6/19 - Amer to Cofirm the date 6/5 - Aligned with Felssy and Team to setup for. NGD. using NPM 5/23 -Will be enabled through NSA Enablement activity. Target Date: 6/30 5/20 - Nasreen to check with Felssy and comebackx | 6/26 - Merge Request raised - Jyothish has approved awaiting Felssey's approval
All MFE | T3 Build Issye | Done | SRE Pipeline | Jyothish Kshatri |  |  | GTSGR-235923 | the issue was created 3 hrs ago can not be due in March
All MFE | Sitespeed.io Setup Browse and Configurator, Checkout MFE (Performance budget) | In Progress | NSA Enablement | Amer Khan | 2024-05-17 | 2024-06-30 | GTSGR-237888 | 7/16 - Now redirected to artifactory team 7/15 - Logged a ticket with SRE team per their ask - JIRA ticket. https://onejira.verizon.com/browse/GTSGR-237888 for resolving issue to download the NPM modules and sitespeed.io 7/12 Currently blocked by problem downloading NPM packages into the containter, reached out to SRE team for help on solution. 7/10 The original solution did not work as it was running sitespeed in the same container as the web site. Testing a new approach will have an update EOD Friday or Monday morning on initial testing. Then need 1-2 days to clean it up and go through the MR process. This will most likley require some changes to the Sitespeed.mjs script to make it dynamic for environments 7/8 - Testing pending. Nishant is out today , Pathiban to pick up this task per Amit 7/2 Testing in progress. Nishant needs help from Jyothish 7/2 Access issue resolved , testing in progress 7/1 - Nishant still. dont have access 6/27,28 - Dev complete Nishant need access from SRE for executing script. Nishat to work with Impl Team 6/26 - WIP - No blockers as of now 6/25 - WIP , on track for 6/30. Amer to connect with Rohit L 6/24 - Updates from Amer - workaround for sitespeed in progress, need to connect with jyothish, good shape by tomorrow morning 6/20 - 1. Tarun / Ashwin to check and remove dependency on npm so that this can be run on CD 2. Amit to check with Felssy if this will be a Gating Check 6/19 - Amer to Cofirm the date 6/5 - Aligned with Felssy and Team to setup for. NGD. using NPM 5/23 - Will be enabled through NSA Enablement activity. Target Date: 6/30 | Sitespeed job to be triggered after SOE and NGD code deploye based on the schedule. To start with this will not be gating check.
All MFE | Axe Core Setup Browse and Configurator,Checkout MFE ( included part of sitespeed setup) | In Progress | NSA Enablement | Amer Khan | 2024-05-17 | 2024-06-30 |  | 7/16 - Now redirected to artifactory team 7/15 - Logged a ticket with SRE team per their ask - JIRA ticket. https://onejira.verizon.com/browse/GTSGR-237888 for resolving issue to download the NPM modules and sitespeed.io 7/12 Currently blocked by problem downloading NPM packages into the containter, reached out to SRE team for help on solution. 7/10 The original solution did not work as it was running sitespeed in the same container as the web site. Testing a new approach will have an update EOD Friday or Monday morning on initial testing. Then need 1-2 days to clean it up and go through the MR process. This will most likley require some changes to the Sitespeed.mjs script to make it dynamic for environments 7/8 - Testing pending. Nishant is out today , Pathiban to pick up this task per Amit 7/2 Testing in progress. Nishant needs help from Jyothish 7/2 Access issue resolved , testing in progress 7/1 - Nishant still. dont have access 6/27,28 - Dev complete Nishant need access from SRE for executing script. Nishat to work with Impl Team 6/26 - WIP - No blockers as of now 6/25 - WIP , on track for 6/30. Amer to connect with Rohit L 6/19 - Amer to Cofirm the date 6/5 - Aligned with Felssy and Team to setup for. NGD. using NPM 5/23 - Will be enabled through NSA Enablement activity. Target Date: 6/30 | Sitespeed job to be triggered after SOE and NGD code deploye based on the schedule. To start with this will not be gating check.
Services | Gatling Setup for API Performance Testing | Done | NSA Enablement | Amer Khan | 2024-05-17 | 2024-07-10 |  | 7/17 - Anand from from DEV team has confirmed to Dhaya from the SRE team to approve pproval to enable gatling service on onevz-soe-browse-service 7/16 - Gosikan to work with Parthipan . Gatling stage should be run only if unit testing stage is enabled 7/12 - This was validated by Anand from the NGD dev team for Browse Services 7/10 - Build failing due to gatling due to access issue , code reverted. New MR raised 7/8 : Dev and Testing Complete. Pathipan wating on Code Merge L2 Approval. Additional changes pending to enable / disable 7/5 ; Anand was trying to skip Gatling during build through pom.xml and run gatling as separate stage but it is is not working, now we have to make condition in unified pipeline script for the applications using gatling, should be completed by Jul 10th. 7/2 ; Initial setup compelte, woild need some addional changes to pom.xml to make it generic. 6/26 - Amit to come back with the ETA on this 6/25 - WIP , plan to integrate in CI. If any help needed from dev reach out to Tarun Jain duriing IST hours 6/21 - Aligned to use Gatling , confirmed with Sasha. We will not be using jenkins plug in 5/23 Discussed with Vamsi. Vamsi to comeback with plan | 6/21 - We are now aligned to use Gatling, as we will not be using the Jnkins plugin. The goahead on the usage of Gatling was also confirmed by Sasha from Felssy's team 6/19- Amit Raut to discuss and come back on api perfromance testing tool recommendation by Monday 6/24. Confirm if we can use Gatling
CDN | Lower Env CDN Setup - SIT T1, T2, T3 | In Progress | SRE Implementation | Vamsi Kalluri/ Bhupendra Madduru | 2024-05-17 | 2024-06-30 | GTSGR-210726. | 8/22 - T2 aalso complete, T1 Pedning 7/25 - T3 Setup Complete, validqation in progress 6/6 Cahnges are working in QA3 with host entry. Planning for 6/11 change for DNS as per Vamsi 6/19 - Had a meeting today with Vamsi , follow up meeting required with @Bhupendra Madduru 5/23 Discussed with Vamsi. Vamsi to comeback with plan | Polina Grosman- Please review this ticket as well
Configurator MFE | Configurator MFE Repo Trunk based setup (build and deploy) | In Progress | SRE Pipeline | Felssy Antoni | 2024-05-10 | 2024-06-30 | GTSGR-195909 | 7/25 - Merged the code in trunk and shared with SRE team. Trunk based pipeline validation in progress by SRE team. Team currently continuing release-based branching 6/3 - Felssy to confirm ETA on testing and when we can switch 6/28 - Code merged to trunk waiting for SRE team to validate and confirm the plan for switch. 6/25 - Yet to be setup 7/9 - finaized env for pipeline testing (to finish by 7/12)
Checkout MFE | Checkot MFE Repo Creation https://gitlab.verizon.com/CV9V_UI/onevz-soe-digital-ngd-checkout | Done | SRE Pipeline |  |  |  | GTSGR-195909
Checkout MFE | Checkout MFE Intitial Code Commit with Build Scripts and Docker info | Done | Dev Team | Sanjeev Kumar Chauhan |  |  |  | Done
Checkout MFE | Checkout MFE Build Job | Done | SRE Pipeline | Jyothish Kshatri | 2024-06-14 | 2024-06-19 | GTSGR-195909 | 6/19 - Build Pipeline not available for Release/24.09.100 6/17- Latest code is not deployed, DIT, SIT URLs are not working. Build is failing |  | As per iniitial discussions this was a 2d task but taking well over a week or 2 or month and with issues
Checkout MFE | Checkout MFE Deploy Setup | Done | SRE Pipeline | Jyothish Kshatri | 2024-06-14 | 2024-06-19 | GTSGR-195909 | 6/19 - Build Pipeline not available for Release/24.09.100 6/17- Latest code is not deployed, DIT, SIT URLs are not working. Build is failing
Checkout MFE | Checkout MFE EKS Setup DIT2 | Done | SRE Pipeline | Jyothish Kshatri | 2024-06-14 | 2024-06-19 | GTSGR-195909 | 6/19 - Build Pipeline not available for Release/24.09.100. Latesst code not deployed 6/17- Latest code is not deployed, DIT, SIT URLs are not working. Build is failing
Checkout MFE | Checkout MFE EKS Setup SIT2 | Done | SRE Pipeline | Jyothish Kshatri | 2024-06-14 | 2024-06-19 | GTSGR-195909 | 6/19 - Build Pipeline not available for Release/24.09.100. Latesst code not deployed 6/17- Latest code is not deployed, DIT, SIT URLs are not working. Build is failing
Checkout MFE | Checkout MFE Ingress Changes DIT2/SIT2 - /nextgendigital/sales/checkout | Done | SRE Implementation | Jyothish Kshatri | 2024-06-14 | 2024-06-19 | GTSGR-188009 | 6/19 - these 2 urls not opening(not reachable) https://soe-hivv-nssit2-bg.ebiz.verizon.com/nextgendigital/sales/checkout https://soe-hivv-nsdit2.ebiz.verizon.com/nextgendigital/sales/checkout
Checkout MFE | Checkout Scheduler for Code Deployment | Done | SRE Pipeline | Jyothish Kshatri | 2024-06-14 | 2024-06-19 | GTSGR-195909 | 6/19 - Build Pipeline not available for Release/24.09.100. 6/17- Latest code is not deployed, DIT, SIT URLs are not working. Build is failing | Enable auto deployment for 24.9.100
Checkout MFE | Checkout MFE Unit Testing Pipeline setup | Done | SRE Pipeline | Jyothish Kshatri | 2024-06-14 |  | GTSGR-195909 | 6/19 - Will validate once latest code is deployed
Checkout MFE | Chekout MFE Sonar setup on Pipeline | Done | SRE Pipeline | Jyothish Kshatri | 2024-06-14 |  | GTSGR-195909 | 6/19 - Will validate once latest code is deployed
Checkout MFE | Checkout MFE fortify setup on Pipeline | Done | SRE Pipeline | Jyothish Kshatri | 2024-06-14 |  | GTSGR-195909
Checkout MFE | Checkout MFE Sysdig - Image Scanning | Done | SRE Pipeline | Jyothish Kshatri | 2024-06-14 |  | GTSGR-195909
Checkout MFE | Checkout MFE Repo Trunk based setup (build and deploy) | In Progress | SRE Pipeline | Felssy Antoni | 2024-06-14 | 2024-06-30 | GTSGR-195909 | 6/3 - Will start this once checkout is validated 6/25 - Yet to be setup 7/9 as item #55
Checkout MFE | Checkout MFE EKS Setup T1 (DIT and SIT) | Done | SRE Pipeline | Jyothish Kshatri | 2024-06-21 | 2024-06-30 | GTSGR-195909 | 6/25. - DIT1 - https://soe-hivv-nsdit1.ebiz.verizon.com/nextgendigital/sales/checkout/health not working Pods are up and running for both SIT1 and DIT1 - 14/06 | Felssy to confirm Date with Implementation team for ingress change
Checkout MFE | Checkout MFE Ingress Changes DIT1/SIT1 - /nextgendigital/sales/checkout | Done | SRE Implementation | Jyothish Kshatri | 2024-06-21 | 2024-06-30 | GTSGR-188009 | 6/25. - DIT1 - https://soe-hivv-nsdit1.ebiz.verizon.com/nextgendigital/sales/checkout/health not working JayKumar confirmed the Urls are up and running in NGD channel- 20/06
Checkout MFE | Checkout MFE EKS Setup T3 (DIT and SIT) | Done | SRE Pipeline | Jyothish Kshatri | 2024-06-21 | 2024-06-30 | GTSGR-195909 | 6/25, 7/1 - DIT3 - https://soe-hivv-nsdit3.ebiz.verizon.com/nextgendigital/sales/checkout/health - Not working SIT3 - https://soe-hivv-nssit3.ebiz.verizon.com/nextgendigital/sales/checkout/health - Not working SIT3 BG - https://soe-hivv-nssit3-bg.ebiz.verizon.com/nextgendigital/sales/checkout/health - Not working (edited) Configuration changes are done. Middleware team confirms scheduler not in place for T3. They are planning for 24.10.100 - 26/06 | Felssy to confirm Date with Implementation team for ingress change. Vidya Sagar
Checkout MFE | Checkout MFE Ingress Changes DIT3/SIT3 - /nextgendigital/sales/checkout | Done | SRE Implementation | @Veerakarthik Achari Kammara @Rohith Kumar @Vishnuvardhan Katla | 2024-06-21 |  | GTSGR-188009 GTSGR-229665 | 6/25, 7/1 DIT3 - https://soe-hivv-nsdit3.ebiz.verizon.com/nextgendigital/sales/checkout/health - Not working SIT3 - https://soe-hivv-nssit3.ebiz.verizon.com/nextgendigital/sales/checkout/health - Not working SIT3 BG - https://soe-hivv-nssit3-bg.ebiz.verizon.com/nextgendigital/sales/checkout/health - Not working (edited)
Checkout MFE | Configurator MFE EKS Setup T4 (DIT and SIT) | Not Started | SRE Pipeline | Jyothish Kshatri | 2024-06-21 |  | GTSGR-195909 | For T4 there is no scheduler is available. It can be deployed using adhoc job. Configuration set-up for T4 is available.
Checkout MFE | Configurator MFE EKS Setup T5 (DIT and SIT) | Not Started | SRE Pipeline | Jyothish Kshatri | 2024-06-21 |  | GTSGR-195909 | Won't be deployed in T5 because we don't have the DIT5, SIT5

## ProdSRE
Env | App | Open Item | Status | Team | Owner | Canary Day | Prod Date | Ticket | Comments | Updated Due date | Next Step
Prod and Canary | Checkout abd Configurator MFE | CDN Routing configurations | Done | CDN | Arthur Beers Fowler IV | 2024-07-12 | 2024-07-16 | GTSGR-233802 | 7/15 - Art will push this change tonight
Prod and Canary | Checkout and Configurator MFE | CDN Caching configurations | Done | CDN | Arthur Beers Fowler IV | 2024-07-12 | 2024-07-16 | GTSGR-233779 | 7/15 - Art will push this change tonight
Prod and Canary | Checkout and Configurator MFE | IG Changes for NGD | Done | IG | Rajesh Mathiyalagan | 2024-07-12 | 2024-07-16 | /IAMIFG-2906
Prod and Canary | Checkout and Configurator MFE | Apigee Changes for NGD | Done | SRE Middleware / Apigee | Divya Chaitanya Prabhu Barlapudi Vijender Pingili | 2024-07-12 | 2024-07-16 | GTSGR-236098 | 7/16 hivv-soe-security-dc-persist-policies-sharedflow needs to be deployed
Prod and Canary | Checkout MFE | Checkout MFE Prodution EKS Deployment Pipeline | Done | SRE Pipeline | Felssy Antoni | 2024-07-12 | 2024-07-16 | GTSGR-234225
Prod and Canary | Checkout MFE | Checkout Code Deployment | Done | SRE Middleware | Srivatsan Kannan Vinod Kumar (Vinod) Rautwar Parag Madhukar Choudhari | 2024-07-12 | 2024-07-16 | GTSGR-234219 | 7/16 - west url is not working https://soe-eks-prod-awswest.vpc.verizon.com/nextgendigital/sales/checkout/health 7/9 - CICD MW team validated the Pipeline. We will provide confirmation once ingress is ready. Until then Marking the status as Pending for Ingress Changes 7/9 - Parag to check with Felssys team and confirm Awaiting deployment details for Canary/Prod from Pipeline team( Felssy's team) 7/8 - Concern with with going with ER due to sre resourse bandwith , request to go with MR - Mahender Akula
Prod and Canary | Checkout MFE | Checkout MFE Ingress Changes | Done | SRE Implementation | Hector Hernandez Rajendra Kunkur Naveen Bhukya | 2024-07-12 | 2024-07-16 | GTSGR-234213 | Rajendra Kunkur
Prod and Canary | Configurator MFE | Configurator MFE Prodution EKS Deployment Pipeline | Done | SRE Pipeline | Felssy Antoni | 2024-07-12 | 2024-07-16 | GTSGR-234225
Prod and Canary | Configurator MFE | Configurator Code Deployment | Done | SRE Middleware | Srivatsan Kannan Vinod Kumar (Vinod) Rautwar Parag Madhukar Choudhari | 2024-07-12 | 2024-07-16 | GTSGR-234219 | 7/16 - west url is not working https://soe-eks-prod-awswest.vpc.verizon.com/nextgendigital/sales/configurator/health 7/9 - CICD MW team validated the Pipeline. We will provide confirmation once ingress is ready. Until then Marking the status as Pending for Ingress Changes 7/9 - Parag to check with Felssys team and confirm Awaiting deployment details for Canary/Prod from Pipeline team( Felssy's team) 7/8 - Concern with with going with ER due to sre resourse bandwith , request to go with MR - Mahender Akula
Prod and Canary | Configurator MFE | Configurator MFE Ingress Changes Production | Done | SRE Implementation | Hector Hernandez Rajendra Kunkur Naveen Bhukya | 2024-07-12 | 2024-07-16 | GTSGR-234213
Prod and Canary | Checkout and Configurator MFE | NGD Logs not rolling | Done | PCT191-Systems Engineering |  |  |  | GTSGR-237227
Prod and Non Prod | Checkout and Configurator MFE | SRE Dasboard (Catch Point Scipting for NGD Flow | Done | SRE | Pandiarajan Gurusamy <pandiarajan.gurusamy@verizon.com>

## Browse MFE -ecomstage
App | Open Item | Status | Team | Owner | Ticket | Due Date | Remarks | Next Step
Browe MFE | EKS Onboarding / Pipeline Setup | Not Started | SRE Pipeline | Felssy Antoni | GTSGR-313790
Browe MFE | IG Changes | Not Started | IG |  | IAMIFG-5227
Browe MFE | Code Deployment | Not Started | SRE Middleware |  | GTSGR-313793
Browe MFE | Ingress Changes | Not Started | SRE Implementation |  | GTSGR-313794
Browe MFE | Apigee Changes | Not Started | SRE Middleware / Apigee
Browe MFE | CDN Routing/ Cache configurations | Not Started | CDN
Services to be setup
https://ecommstage.verizon.com/nextgendigital/browse/health

## Browse MFE - ProdSRE
Env | App | Open Item | Team | Owner | Ticket | Canary, Prod Status | eComStage Status | Comments | Updated Due date | Next Step
Canary, Prod and eComStage | Browse MFE | Browse MFE Prodution EKS Deployment Pipeline | SRE Pipeline | Srivatsan Kannan Arun Arumugachamy | GTSGR-313790 | Done | Not Done | https://ecommstage.verizon.com/nextgendigital/sales/browse/health is not working
Canary, Prod and eComStage | Browse MFE | Browse MFE Code Deployment | SRE Middleware | Srivatsan Kannan Arun Arumugachamy | GTSGR-313793 | Done | Not Done
Canary, Prod and eComStage | Browse MFE | Browse MFE Ingress Changes | SRE Implementation | Srivatsan Kannan, Hari Kothapalli, Selvaraj Anthoniammal, Chockalingam D, Naveen Bhukya | GTSGR-324500 | Done | Not Done | Ingress changes done in Non prod in https://onejira.verizon.com/browse/GTSGR-323826. Similar changes to be done in Prod.
Canary, Prod and eComStage | Browse MFE | IG Changes for NGD Browse MFE | IG | Rajesh Mathiyalagan | IAMIFG-5227 | Need confirmation | Need confirmation | This may not need any change on Prod , just need confirmation
Canary, Prod and eComStage | Browse MFE | Apigee Changes for NGD Browse MFE | SRE Middleware / Apigee | Divya Chaitanya Prabhu Barlapudi |  | Need confirmation | Need confirmation | This may not need any change on Prod , just need confirmation
Canary, Prod and eComStage | Browse MFE | CDN Routing configurations | CDN | Jeremy S Lichtman |  |  |  | To be done once MFE is Setup
Canary, Prod and eComStage | Browse MFE | CDN Caching configurations | CDN | Jeremy S Lichtman |  |  |  | To be done once MFE is Setup

## Logged in SSR
App | Task | Ticket | Prod Ticket | Status | Team | Owner | Due Date | Comments | Next Step
All NGD | IG Changes to support Logged in API calls from Next.js SSR | IAMIFG-5516 |  | System Test | IG
All NGD | Apigee Changes to support Logged in API calls from Next.js SSR | GTSGR-323982 | GTSGR-331076 | System Test | APIGEE

## Streaming
App | Task | SIT Ticket | Prod | Status | Team | Owner | Due Date | Comments | Next Step
NGD All Apps | Akamai - Enable Streaming at | GTSGR-321116 |  | In Progress | SRE | Arthur Beers Fowler IV
NGD All Apps | IG - Enable Streaming | IAMIFG-5402 |  | System Test | IG |  |  | Streaming working in DIT3 , there was a 504 issue which got resolved https://vzwqa30.verizonwireless.com/nextgendigital/sales/configurator/devices/smartphones/apple-iphone-15/dev21410694/MTLY3LL%2FA
NGD All Apps | Apigee - Enable Streaming | GTSGR-307902 | GTSGR-331077 | System Test |  |  |  | Need ticket Info , change are aleady done in non prod

## ecomstage
App | Open Item | Status | Team | Owner | Ticket | Due Date | Remarks | Next Step
Checkout and Configurator MFE | EKS Onboarding / Pipeline Setup | Done | SRE Pipeline | Felssy Antoni | GTSGR-251266 | TBD | 8/27 Note from Felssy - The pipelines are already created. We don't have separate pipelines for staging. You just have to configure the values for staging. Please do those changes and take it forward.
Checkout and Configurator MFE | IG Changes | Done | IG | Rajesh Mathiyalagan | IAMIFG-3612 | TBD | 8/27 : Rajesh is checking this with Infra on this, he will provide an update
Checkout and Configurator MFE | Code Deployment | Done | SRE Middleware | Srivatsan Kannan Choudhari, Parag Madhukar | GTSGR-251267 | TBD | 8/27 Note from Felssy - The pipelines are already created. We don't have separate pipelines for staging. You just have to configure the values for staging. Please do those changes and take it forward. Pending for pipeline creation , dependent on GTSGR-251266
Checkout and Configurator MFE | Ingress Changes | Done | SRE Implementation | Naveen Bhukya D, Chockalingam | GTSGR-251268 | TBD
Checkout and Configurator MFE | Apigee Changes | Done | SRE Middleware / Apigee | Divya Chaitanya Prabhu Barlapudi | GTSGR-263802 | Done | Discussed with Chaitanya, there is no change required here
Checkout and Configurator MFE | CDN Routing/ Cache configurations | Not Started | CDN | Jeremy S Lichtman |  | TBD | We will creeate a ticket for this task once the applicaton is up an running in stage
NGD Browse repo | SRE changes | Done | SRE Implementation | Chockalingam D | GTSGR-343655 | Done | Enable browse repo for the ecommStage env.
Services to be setup
https://ecommstage.verizon.com/nextgendigital/sales/configurator/health
https://ecommstage.verizon.com/nextgendigital/sales/checkout/health

## T5&6
App | Task | T5 Configurator Status | T5 Checkout Status | T6 Configurator Status | T6 Checkout Status | Team | Owner | Ticket | Due Date | Remarks | Next Step
Checkout & Configurator | EKS Onboarding / Pipeline Setup | Not Started | Not Started | Not Started | Not Started | SRE Pipeline | Felssy Antoni | GTSGR-276074
Checkout & Configurator | IG Changes | Not Started | Not Started | Not Started | Not Started | IG | Rajesh Mathiyalagan | IAMIFG-3968
Checkout & Configurator | Code Deployment | Not Started | Not Started | Not Started | Not Started | SRE Middleware | Srivatsan Kannan Choudhari, Parag Madhukar | GTSGR-276075
Checkout & Configurator | Ingress Changes | Not Started | Not Started | Not Started | Not Started | SRE Implementation | Naveen Bhukya D, Chockalingam | GTSGR-276076
Checkout & Configurator | Apigee Changes | Not Started | Not Started | Not Started | Not Started | SRE Middleware / Apigee | Divya Chaitanya Prabhu Barlapudi | GTSGR-276077 |  | NO Changes needed.
Checkout & Configurator | CDN Routing/ Cache configurations | Not Started | Not Started | Not Started | Not Started | CDN | Jeremy S Lichtman

## Other
Open Item | Status | Owner | Next Step | Due Date
Next.js Approval from EA | Closed | Arun | Rajneesh to talk to Naveen 3/7- Add Shiv to Loop - Done 3/8 - Still waiting on approval from EA, Rajneesh is following up with Naveen 3/13 - Meeting setuo for 3/14 to discuss feedback 3/14 - Closed with EA on using Next.js | 2024-03-08
MFE Approach and Poly vs Mono - Alignment | Closed | Joseph Magner | 3/7 - Offshore team to connect with Dinesh to document concerns 3/8 - Dinesh and Offshore team connected. Final approach to be aligned on 3/11. 3/11 - Aligned with Dinesh, Soma on using Poly approach (separate repo for global common, buy repo, manage repo) | 2024-03-08
AEM Dev R&R | Closed | Arun P Bhikawat | Call with Karyn Lewis 3/6 - Done (aligned on that AEM component development will be done by FED Dev team - Karyn's team) RISK: The timeelines are not shared by her awaiting the final design. FED's timeline to be aligned to match NGD Arun to talk to Vikram V 4/30 - Browse work is out of scope and any AEM work will be done by FED Team | 2024-03-12
Alignment of Dependent teams for ACT ( SOI AEP NBX Fusion EA Down Stream System etc) For story grooming feasibility , development | Closed | Rajneesh K Burra | 3/7 - Aligned with SOI - POC - Nevena Nikolaeva 3/7 Aligned with AEP - POC - Rajkumar Williams 3/8 Rajneesh following up with YS on NBX team alignmen for NGD 3/14- Met wih NBX team today | 2024-03-15
Meeting Regaring WAST and Sentry | Closed | Ashwin Raj | Call Scheduled for 3/8 3/8 - Met with Sudheer Adumulla. Sudheer to Provice access to SENTRY Connect with Paul G to understand rules setup on Sentry and Wast. Ashwin to setup a call with Paul next week | 2024-03-15
Edg.io Security Documentation | Closed | Ashwin Raj | Waiting response from Edg.io 3/8 - Sent followup note to Edg.io for Security documentation and Logging 3/13 - Got a response but not documentatoin on security yet | 2024-03-15
Alignment of MFE approach with Assisted Team | Closed | Arun P Bhikawat | 3/11 - as per meeting with Pranay 4/30 - Final meeting setup for 5/2 | 2024-03-20

## Edgio
App | Open Item | Status | Team | Owner | Due Date | Ticket | Comments | Updated Due date | Next Step
Edgio | Edgio security review | In Progress | Security | Chaitanya / Vijendar | 2024-06-30 | PCM-39664